## Slide 1: Project Plan V3.0 for the ICD Revision
ICD Revision Process: Beta Phase and Finalization
Dr. Anni Preisler
Dr. Molly Meri Robinson Nicol

## Slide 2: Introduction
As per the meeting on the Joint Linearization for Mortality and Morbidity Statistics (December 2013), WHO decided to update the Project Plan based on new information and timelines
Key documents
  ”ICD Revison Process: Beta Phase and Finalization”
  ”ICD-11 BETA 2013 Annotation Document”
  Previous Project Plan Drafts (2007-2010-2012)

## Slide 3: Methods
Software program: Microsoft Project
The Project Plan was designed backwards
  An inflexible deadline of submitting the revised ICD in May 2017
Potential issues: the fact that tasks often take longer than originally projected
  Identifying those tasks that are most essential to completing the core requirements of the project on time
A single, joint Project Plan
  To maintain a common, high-level overview, to allow for the identification of the interdependencies
  To limit the need to review multiple documents
  This was decided even though there are some tasks so complex and detailed that they might easily constitute a project plan in and of themselves, such as the review process or field trials

## Slide 4: Results
A document that suits multiple use cases, and that can be provided in a variety of formats
One slide overview (a.k.a. Gantt/Calendar View)
Task version(s)
  Useful, particularly for tasks 2 and 6, each of which include a very high level of granularity, number of subtasks, and associated details. Each TASK has an individual output.
Master version
  All tasks together (13 major tasks, at present)
  Comprehensive overview
    This includes all of the detail from the Project Plan together with references to previous iterations, history of the revision, and other relevant and associated information

## Slide 5: Conclusion
The purpose of the project plan update was:
  Detailed information on new and modified streams of work, activities and tasks
  Updated start and finish dates as well as intermediate milestones
  Fully specified interdependencies between tasks
  Formal designation of responsible persons/required resources
  Updated mechanisms for reporting results and deliverables
As a living document, update of the Project Plan
will remain an ongoing process

## Slide 6: Acknowledgments
We would like to specifically acknowledge and thank
The different Collaborating Centres and the RSG-SEG who participated in the development of the Project Plan, and gave their constructive feedback.

## Slide 7: Summary Timeline

## Slide 8: TASK 1: Generating multiple ICD Linearizations & initial internal review
Key Tasks
● | “Tidy the linearization” | 31 May 2014
● | M & Mb TAG review - Phase 1 | 
● | National Linearizations: Review by National Modifications owners & Stability Analysis | 
● | Verbal Autopsy Linearization | 
● | Primary Care Linearizations | 30 June 2014
● | Specialty Linearizations | 30 June 2015
Responsible Officer(s)
  CTS Team, in general
Interdependent with Task 2 (Reviews), Task 5 (Beta Proposal Mechanisms) and Task 6 (Field Trials)

## Slide 9: TASK 2: Conducting external peer reviews
Key Tasks
Responsible Officer(s)
  Molly Meri Robinson Nicol
Looking for partners to engage in evaluating various aspects of ICD and the revision, including:
  Reviewers
  Proposal Authors
  Individuals to engage in, conduct, and coordinate field trials
  Users to provide feedback on requirements
Initial Reviews | 29 May 2015
Final Reviews | 30 June 2016

## Slide 10: TASK 3: Developing the Reference Guide Knowledgebase
Key Tasks
Responsible Officer(s)
  Robert Jacob
DRAFT Print Reference Guide | 31 May 2014
Reference Guide, second draft | 30 September 2014
Editing, Updates and finalization of Reference Guide | 31 October 2016

## Slide 11: TASK 4: Developing the ICD Index
Key Tasks
Responsible Officer(s)
  Can Celik and Robert Jakob
Digital Index for ICD 11 Beta | 31 May 2014
Print Index for ICD 11 Beta | 
Field testing of ICD 11 Beta Index | 1 October 2016

## Slide 12: TASK 5: ICD Beta Proposal Mechanisms
Key Tasks
Responsible Officer(s)
  Molly Meri Robinson Nicol
Interdependent with Task 2 (Reviews)
Start public proposal mechanism in the ICD Browser | 2 June 2014
Link proposal mechanism with review process | 13 March 2015

## Slide 13: TASK 6: ICD Beta Field Trials
Key Tasks
Responsible Officer(s)
  Nenad Kostanjsek
Interdependent with Task 1
  Task 6 involves many subtasks, therefore the full granularity will be represented in a parallel, fully linked and interconnected Project Plan.
Pilot Phase | 31 October 2014
Main Phase | 1 October 2016

## Slide 14: TASK 7: Producing ICD in Multiple Languages
Key Tasks
Responsible Officer(s)
  Can Celik and Robert Jakob
Ongoing task
Coordinate translation process in official WHO languages and others (First draft) | 30 September 2014
Implement Quality Assurance Protocol | 31 October 2014

## Slide 15: TASK 8: Transition Preparations
Key Tasks
Responsible Officer(s)
  Tevfik Bedirhan Ustun and Molly Meri Robinson Nicol
The increased focus and work under Task 8 is a direct response to the concern the different member states raised in the WHO-FIC meeting 2013, and the main outcome will be to identify future challenges and solutions, and to make the transition from ICD10 to ICD 11 as smooth as possible.
Pilot interview | 31 May 2014
Second round of interview | 31 October 2014
Third round of interview | 31 July 2015
Transition preparations finished | 31 October 2016

## Slide 16: TASK 9: Submitting the ICD to WHO Governing Bodies
Key Tasks
Responsible Officer(s)
  Tevfik Bedirhan Ustun and CTS team
Interdependent with all the other tasks
Preparing the submission package | 30 April 2016
Availability in six official WHO languages | 1 October 2016
Submission to Executive Board of WHO | 1 November 2016
Submission to World Health Assembly | 1 March 2017
Official Release of ICD-11 | 1 November 2017

## Slide 17: TASK 10: Maintenance & continuous update of ICD after WHA approval
Key Tasks
Responsible Officer(s)
  Tevfik Bedirhan Ustun and CTS team
Interdependent with Task 9
Complete ICD-11 update and revision | 29 September 2017
Maintenance platform for ICD | 
Update mechanism – Transition from RSG to URC | 

## Slide 18: TASK 11: Computerization & Software Development Tasks
Key Tasks
    iCAT core software maintenance and update
    Browser maintenance and update
    Stability Program
    Dashboard(s)
    Index applications
    Proposal Mechanism
    Multi-lingual (Translation Tool) maintenance and update
    Social Computing strategy & implementation
    Field Trials web platform
    URI services
    Update and maintenance of the Knowledgebase Software
    Update and maintenance of the Review Platform
Responsible Officer(s)
  Can Celik
This are not independent task, but a collection of "Computerization & Software Development Tasks” from Tasks 1-12. They are reiterated here in summary for easy review.

## Slide 19: TASK 12: Communication and Information Dissemination
Key Tasks
    WHO Web sites
    Annotation Document
    Information Notes
    Active information sharing with stakeholders
      Project Plan
      User groups
      Social Computing push
    Continuous Evaluation and improvement of the ICD Communication Strategy
Responsible Officer(s)
  Tevfik Bedirhan Ustun

## Slide 20: TASK 13: Meetings
WHO-FIC Network Annual Meetings
  Barcelona 2014, London 2015, Tokyo 2016 and Mexico 2017
Annual meetings with identified stakeholders
  Spring 2015 and 2016
ICD 11 Project Plan
  thorough bi-annual update